ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Romania and Ukraine within the Joint Operational Programme Romania-Ukraine 2014-2020

## Contracting Authority

”VASILE GOLDIȘ” University Foundation of Arad, Branch of Satu Mare, 26, Mihai Viteazu street, Satu Mare

## Country background

This TOR is concluded for DNA sequencing services in order to adequately implement part of the activities assumed within the framework of GRANT CONTRACT for the PROJECT 2SOFT/1.2/48, entitled PARTNERSHIP FOR GENOMIC RESEARCH IN UKRAINE AND ROMANIA, under THE JOINT OPERATIONAL PROGRAMME ROMANIA-UKRAINE 2014-2020, financed by ENI-CBC.

Project Summary:

The project proposes to join the expertise and the resources of our two partnership institutions to build a comprehensive approach to study genome sequence in 300 human DNA samples to describe variation and population structure underlying health and treatment outcomes in a genetically diverse population along the border between Romania and Ukraine.  As the worldwide trend to personalized medicine continues, researchers in Romania and Ukraine should be able to contribute to the study of regional populations to ensure that as a result of these studies, the local patients will be able to access to cutting-edge treatments in the nearest possible future.  In the process, the project will benefit by providing the opportunity for training, collaboration and innovation in both countries.

This project provides a real opportunity to close one of the largest remaining gaps on the map of genome variation in Europe, and provide a solid foundation for the future studies of genome variation in the area.

Recognizing an enormous need to develop local expertise in genomics and bioinformatics in the target area, we will train the next generation of young researchers and health professionals capable to meet the emerging challenge of genome technology and big data analysis.  This project will specifically address the training of young scientists in a series of intensive workshops, develop curriculum and training faculty to build joint educational capacity, and will disseminate the knowledge and the data acquired in this project to the wide range of biomedical experts.

Training the next generation of genomicists and bioinformaticians in the border region between Ukraine and Romania will help address the lack of regional  research for several reasons. First, local students tend to concentrate on critical research involving conditions and diseases that disproportionately affect regional populations, such as the ones living along the borders of our two countries. Second, their cultural competency can help in the recruitment and retention of research participants, addressing a crucial need for genomics and bioinformatics research in the local  populations.

Project Outputs Targeted by this TOR:

- Extracted High molecular weight DNA samples;

-Whole genome sequence data;

-Accessable sequence data in the form of the online database;

- -Peer review paper describing the data collected during the project.

## Current situation in the sector

This project will contribute to the development of the unified common European research area, where scientific knowledge, technology and researchers move freely, and contribute to engaging trans-border cooperation between scientists in a member state (Romania) and associated state (Ukraine).  Specifically, the project will contribute to building the research capacity in the trans-border region, developing more research and engineering talent contributing to the genomics research in the area.  The results of this project will be used to address health issues, and contribute to closing the gap in health related research and health care disparities with the richer countries.  Specifically, local medically related genome variants will be discovered contributing to our understating of genetic factors involved in infectious diseases such as HIV/AIDS

The project will make a special care to promote women's participation in science, by ensuring that women are equally represented at each level from management to direct research participants and well as among the workshop attendees. Finally, described activities will create job and research opportunities for students and young faculty members.

## Related programmes and other donor activities

The proposed sampling method has previously been successfully implemented in previous studies such as "1000 Genomes" Project, and other national genome projects.  This dataset will represent a unique and valuable collection of genetic information contribution to our understanding of human variation around the globe, and giving a local perspective to the human variation across the region.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

We will resequence, assemble and annotate chromosome structures and functional elements in 300 human genomes sampled across the border between Romania and Ukraine.  This data will be accessible through a designated public web-server to be available for the researchers and health professionals by the end of the study (18 months).

We will make our 300 genomes database accessible to the researchers and health professionals, as well as the members of general public. This will achieved through the developing two custom informatics tools.  The first set of tool will help identify and describe common, rare, and endemic medically-relevant mutations in the ethnically diverse human population of the region.

The second set of tools will serve medical communities in planning the future clinical research by allowing for unbiased mutation identification in the local samples.  Specifically, this will be designed to be used  in medical genetics, clinical cohort selection, and contribute to the innovation in the field of personalized medicine in the region.  The tools will be presented to the local research and health community at the Final Conference (18 months) and will be submitted as two peer-reviewed publications.

## Purpose

The purpose of this contract is as follows: to sequence 150 human DNA samples for the whole genome.

## Results to be achieved by the Contractor

- 150 fully sequenced human DNA samples (whole genome/sample)

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

NA

## Risks

COVID-19 restriction regarding the blood collecting samples, regarding the pandemic changing rules of the project documents between partners by mail (in hard copies), or between the contracting authority and the contractor, the sending of biological samples, etc.

# SCOPE OF THE WORK

## General

### Project description

Implementation of actions described at 4.2

### Geographical area to be covered

According to point 1.1. above

### Target groups

Lot 1 – 300 persons (Ukraine and Romania) which will have the entire genome analyzed.

Lot 2 – Researchers and technical personnel from Romania and Ukraine, which will be trained in collection, consent, molecular techniques in DNA analysis (6 senior and 17 technical personnel)

Lot 3 – Students, researchers participating in the workshops “Genomics and Bioinformatics in Medical research” and conferences (30 students – 15 for each country will be exposed to both the teoretical and practical hands-on experience in genomics and bioinformatics.

Lot 4 – All residents of the cross-border regions and citizens of both countries in general, especially people with genetic conditions contributing to the risk of infections, chronic and oncological diseases as genetic basis of medical conditions in this region.

## Specific work

### Specifications regarding sample collection provided by the Contracting Authority

The project aim to sequence and annotate human genomes to build a public resource of common genomic variation in the cross-border region between Romania and Ukraine, the Eastern Carpathian Mountains. The sampling strategy was designed to collect 150 samples on each side of the border (300 in total) specifically in Satu-Mare, Baia-Mare and Zakarpattia, to maximize ethnic and geographic diversity, and to capture most medically-relevant genetic variants. We recruited, consented and sample blood collection from adult (>18 years old) volunteers of both sexes, 150 on each side of the RO-UA border. In order to represent the local variation, we studied whose grandparents have been born in the same area. As a result, we will produce the foundation for public reference catalogue of local genome variation, the genome-wide basis for the future genetic studies and personalized medicine in the cross-border region.

Experimental Protocol:

To participate, volunteers must meet the following inclusion criteria:

• to be domiciled in one of the two counties of Satu-Mare or Maramures

• be at least 18 years old and be able to give their informed consent of their own free will;

• volunteer to provide a blood sample so that researchers can obtain their genetic sequence by sequencing or genotyping that DNA;

• allow the use of the sample in a "cell line", an in vitro culture of blood cells obtained from the blood sample that would make it possible for researchers to obtain genetic material from the sample in the long term (possibly in the indefinite future);

• allow the genetic information obtained from this study to be freely accessible in the scientific databases available online. We will never disclose the name or other traditional identifying information that personally correlates the data with the person, such as name, occupation, address and date of birth;

• be willing for many researchers around the world to study the genetic material and data in the sample for an indefinite period of time and for the information obtained by them to be used in scientific databases. Again, the name and any other standard personal identifiers will not be associated with the data from this study. Researchers studying the material and data in the samples will be told only the sex of the medical information provided in the questionnaire and the family history reported by the donor (ethnic or geographical group) and his predecessors.

The decision on participation or study is up to the person and is entirely voluntary.

Target group: a heterogeneous group of subjects, coming from the geographical areas included in the territory of Satu Mare and Maramures county, with a distribution by sex of 50% / 50%, with a more accurate coverage of the entire geographical area

Biological samples taken:,whole blood samples, collected in anticoagulant tubes

Harvesting methodology:

- informing the patient

- obtaining the informed consent of the patient

- obtaining the agreement for the processing of personal data in accordance with the European standards in force on the processing of personal data and their free movement, as provided for in EU Regulation 2016/679

- preparing the patient for the collection of biological samples

- asepsis of the puncture site

- applying the tourniquet and highlighting the vessel to be punctured

- puncturing the harvesting needle caught in the holder

- harvesting of two vacuums with EDTA, which have a purple lid

- identification of the two vacutainers in which the harvest was made by noting the identification number + the initials of the county (MS or MM)

- complete completion of the Centralized Table of Evidence and Questionnaire, regarding age, sex, personal pathological antecedents and heredocolateral antecedents

- after harvesting the samples will be kept at -20˚C

- the transport of the samples will be carried out in ice-cold refrigerated boxes for processing at the Laboratory of the Vasile Goldis Foundation from Satu-Mare, 26 Mihai Viteazu Street, Satu-Mare.

### Specifications regarding DNA extraction from blood samples provided by the Contracting Authority

The DNA from the blood samples were isolated with PureLink® Genomic DNA Kits from Invitrogen which allow rapid and efficient purification of genomic DNA. The PureLink® Genomic DNA Kits are based on the selective binding of DNA to silica-based membrane in the presence of chaotropic salts. The lysate is prepared from a variety of starting materials such as tissues, cells, or blood. The cells or tissues are digested with Proteinase K at 55°C using an optimized digestion buffer formulation that aids in protein denaturation and enhances Proteinase K activity. Any residual RNA is removed by digestion with RNase A prior to binding samples to the silica membrane. The lysate is mixed with ethanol and PureLink® Genomic Binding Buffer that allows high DNA binding PureLink® Spin Column (Mini Kit). The DNA binds to the silica-based membrane in the column or plate and impurities are removed by thorough washing with Wash Buffers. The genomic DNA is then eluted in low salt Elution Buffer. The isolated DNA is 20–50 kb in size and is suitable for PCR, restriction enzyme digestion, and Southern blotting.

Preparing lysates

1. Add 200 μL blood sample (fresh or frozen) to a sterile microcentrifuge tube and supplement it with 20 μL Proteinase K and 20 μL RNaseA and incubate at room temperatue for 2 minutes.

2. Add 200 μL PureLink® Genomic Lysis/Binding Buffer and mix well by vortexing to obtain a homogenous solution.

3. Incubate at 55°C for 10 minutes to promote protein digestion.

4. Add 200 μL 96–100% ethanol to the lysate. Mix well by vortexing for 5 seconds to yield a homogenous solution.

Binding DNA

1. Remove a PureLink® Spin Column in a Collection Tube from the package.

2. Load the lysate (~640 μL) prepared with PureLink® Genomic Lysis/Binding Buffer and ethanol to the PureLink® Spin Column.

3. Centrifuge the column at 10,000 × g for 1 minute at room temperature.

4. Discard the collection tube and place the spin column into a new collection tube.

Washing DNA

1. Wash the column with 500 μL Wash Buffer 1 prepared with ethanol.

2. Centrifuge the column at 10,000 × g for 1 minute at room temperature. Discard the collection tube and place column into a new collection tube.

3. Wash the column with 500 μL Wash Buffer 2 prepared with ethanol.

4. Centrifuge the column at maximum speed for 3 minutes at room temperature. Discard the collection tube.

Eluting DNA

1. Place the spin column in a sterile 1.5-mL microcentrifuge tube.

2. Elute the DNA with 50 μL of PureLink® Genomic Elution Buffer.

3. Incubate the column at room temperature for 1 minute.

4. Centrifuge the column at maximum speed for 1 minute at room temperature. The tube contains purified DNA.

6. Store the purified gDNA at 4ºC for short-term or –20°C for long-term storage.

4.2.3. Tasks to be performed by the Contractor (DNA sequencing for 150 DNA samples – whole genome/sample)

The tasks performed by the Contractor: DNA sequencing services for a number of 150 DNA samples, respectively sequencing of the whole human genome/sample, services funded by the project "Partnership for genomic research in Ukraine and Romania" (2SOFT / 1.2 / 48), funded by the Joint Operational Program Romania-Ukraine 2014 -2020.

The specifications for the tender on sequencing:

Number of DNA samples sequenced: 150

Sequencing technology (sequencer type): Next generation sequencing, Nova Seq, MGISEQ-2000RS, DNBSEQ-G400RS or equivalent

Number of cycles: 150 cycles

Total number of cycles: 300 cycles

The amount of data obtained during one run: at least 100 GB

Genome type: Entire Human genome

Genome coverage: 30 X

Requirements for the length of reads: 150-400 nucleotides

The information will be stored and sent to the Contracting Authority on a high capacity hard disk (2 copies on two hardisks).

## Project management

### Responsible body

The project implementation team of Contracting Authority:

”VASILE GOLDIȘ” University Foundation of Arad, Branch of Satu Mare, 26, Mihai Viteazu street, Satu Mare

### Management structure

Management structure of the Contracting Authority: Project Manager, Assistant Manager, Financial Responsible, Executive Director and Deputy of the Foundation (legal representatives). The Contractor’s report will be approved by the Management team of the project and all payments will be approved by the Legal Representative.

The Contracting Authority will share information and ask for input on the decision making from project leader.

### Facilities to be provided by the Contracting Authority and/or other parties

The Contracting Authority („Vasile Godis” University Foundation of Arad,  Satu-Mare Branch) will send the biological samples (150 extracted DNA) to the location provided by the Contractor. The costs sample transportation will be supported by the Contractor.

# LOGISTICS AND TIMING

## Location

The data stored on 2 copies (2 high capacity hard disks) will be send to the „Vasile Godis” University Foundation of Arad,  Satu-Mare Branch/ Fundatia Universitara „Vasile Goldis” Arad, Filiala Satu-Mare, adress: Satu Mare, Mihai Viteazu str., no. 26, Satu Mare County, Romania, phone: +40 261716220, fax: +40 261716230. The shipping will be supported by the Contractor.

## Start date & period of implementation

The intended start date is date of signature of the contract to October 11, 2021. The period of implementation is foreseen for October 2021 – December 2021. If not possible due to external conditions/situations, the contracting parts will agree upon new terms of execution, but no further than December 15, 2021.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

NA

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion

6.4 Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in Romanian and English in one original and 1 copy:

- Inception Report of maximum 12 pages to be produced after two weeks from the start of implementation. In the report the Contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The Contractor should proceed with his/her work unless the Contracting Authority sends comments on the inception report.

## Interim report (if the case). The contractor can prepare interim reports after providing the services according to the tasks requested by the Contracting Authority. The approval of interim reports by the Contracting Authority will be the basis for issuing interim invoices and making interim payments as indicated in the Special Conditions.

## Draft final report of maximum 12 pages (main text, excluding annexes). This report shall be submitted after the finalization of the activities.

## Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 2 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on services provided. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice. This final report must be approved by the Contracting Authority.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

## The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manner, as required in these Terms of Reference”.

## Special requirements

Not the case.